## Sheet1
STUDY PROGRAMME DEVELOPMENT TAILORED ACTION PLAN and KEY DEADLINES (WP2-WP5, WP7)
|  | 2016 | [8 empty] | 2017
|  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
WP2
Benchmarking reports | 2.1 | 2016 Jun: Jun 30
Consolidated report (LB) | 2.2 | 2016 Aug: Aug 31
Visit to non-project partners (Medicine) | 2.3 | 2016 Nov: Nov 21-25
VIP trip to AAU | 2.4 | 2016 Oct: Oct 3-7
WP3
EU (AAU/UOG) visit to MD | 3.1 | 2016 May: May 23-27
Road maps (6) fit for purpose & Road maps (6) content change | 3.2 | 2016 Oct: Oct 31
Consolidated report (LB) | 3.3 | 2016 Dec: Dec 15
WP4
Finalized PBL-based study program description (6, new structure & content) | 4.1 | 2016 Nov: Nov 30
Submited for approval to relevant bodies | 4.2 | 2017 Jan: Jan 15
Advertize the new study programmes | 4.3 | 2017 Feb: Feb 1
Each team agrees on mobility period (linked to 3.1) | 4.4 | 2016 May: May 30
Mobility Guidelines finlized (LB) | 4.5 | 2016 May: May 30
Mobility Guidelines published (LB) | 4.6 | 2016 Jun: Jun 15
SPTs mobility plans with clear objectives and outputs to LB | 4.7 | 2016 Sep: Sep 15
Mobility strand: MD mobility to EU | 4.8 | 2016 Oct: Oct-Dec
WP5
Sem1: Teaching starts at new study programs | 5.1 | 2017 Sep: Sep-Jan
Mobility strand - CO-TEACHING: EU Staff Mobility to MD | 5.2 | 2017 Sep: Sep-Dec
WP7
Mass-media articles (one per SPT) | 7.1 | 2016 Jun: Jun 15; 2016 Nov: Nov 15; 2017 Mar: Mar 15
Publicity on university websites (2 weeks after an event/activity) | 7.2
Conference Paper submission | 7.3 | 2016 Aug: Aug 31
International conference | 7.4 | 2016 Oct: Oct 27-28