## Sheet1
PBLMD ACTION PLAN Y1-4
| 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Project start date | 2015 Oct: 15
WP2
PBL team to MD | bar: 2016 Jan
MD to AAU | bar: 2016 Feb
MD to UoG | bar: 2016 Mar
MD to KTH | 2016 Sep: W39 (26-30)
MD to SIEGEN | 2016 Apr: W15
MD to Plymouth | 2016 Nov: W47 (20-26)
MD (VIP) to AAU | 2016 Oct: W40 (3-7)
Best practice/experience reports | bar: 2016 Jun to 2017 Jun
Benchmarking reports SP | 2016 Jun: W26: June 30
Benchmarking reports PT | 2016 Nov: W48: Nov 30
Consolidated report SP | 2016 Aug: W35: Aug 31
Consolidated report PT | 2017 Jan: W5: Jan 31
WP3
KTH/SIEGEN to MD | 2016 Nov: W44(Oct31-Nov4)
AAU/UOG to MD | 2016 May: W21
Road maps (6) fit for purpose & Road maps (6) content change - SP | 2016 Oct: W44: Oct 31
Road maps (6) fit for purpose & Road maps (6) content change - PT | 2017 Mar: W13: Mar 31
Consolidated report | 2016 Dec: W50: Dec 15
WP4
Staff Mobility (MD to EU) | 2016 Oct: W43-48; 2017 Jan: W2-5
Advertise new study programs | bar: 2017 Feb
PBL-based study programs (6, new structure & content) SP | 2016 Nov: W48: Nov 30
Submited for approval to relevant bodies (SP) | 2017 Jan: W2: Jan 15
Finalized program desciptions (6) PT | 2017 May: W22:May 31
Submited for approval to relevant bodies (PT) | 2017 Jun: W26: June 30
WP5
Sem1 Teaching/learning outcomes/exams (Staff Mobility EU to MD) | 2017 Sep: Autumn 2017
Sem2 Teaching/learning outcomes/exams (Staff Mobility EU to MD) | 2018 Feb: Spring 2018
Sem3 Teaching/learning outcomes/exams (Student Mobility) | 2018 Sep: Autumn 2018
Sem4 Teaching/learning outcomes/exams (Student Mobility) | 2019 Feb: Spring 2019
WP7
International conference | 2016 Oct: W43 (27-28)
Paper submission | 2016 Aug: W35: Aug 31
WP8
Steering committee meetings | 2016 Oct: W43 (24-26)
Project end date | 2019 Oct: 14
Major Deadlines